## 1.1 Project Team
Core Team or Larger Team? | Full Name | Email | Phone | Occupation/ Title | Organization | Notes

## 1.2 Plans and Efforts
Plan/ Initiative Title | Year Published | Type/ Focus | Plan Contact Name | URL Link | Key sections to reference/ Notes
County Green Hazard Mitigation 5-year Plan | 2015 | Hazard mitigation plan | Jane Doe, County Administration Office | www.google.com | Consider including details about any community strengths (active community-based organizations), local information (GIS resources), community knowledge, preexisting social or economic stressors, or historical land zoning policies.

## 1.3 Timeline
MODIFY AS NEEDED Step | Month, Milestone | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Get Started | Assemble a team | bar: 1
Develop goals | bar: 1
Project timeline | bar: 1
Understand Exposure | Identify hazards and climate stressors | bar: 1
Understand exposure – Create an exposure matrix | bar: 2 to 3
Collect spatial data | bar: 3 to 4
Assess Vulnerability and Risk | Develop rulesets | bar: 4
Preliminary analysis – Create impact statements | bar: 4 to 5
Finalize assessment and develop insights | bar: 5 to 6
Investigate Options | Research/ brainstorm | bar: 6 to 7
Inventory options as a group | bar: 7
Prioritize and Plan | Prioritize | bar: 7 to 8
Plan | bar: 8 to 10
Take Action | Implement | bar: 10 to 11
Monitor/ measure | bar: 11 to 12

## 2.1 People and Community Asset
Theme (https://toolkit.climate.gov/asset) | Types
Agriculture and Food Supply
Aquatic and Marine Resources
Cultural and Community Services
Critical Facilities
Forestry
Economy
Energy and Utilities
Natural Areas and Wildlife
People
Property
Transportation and Mobility
Urban Landscape and Tree Canopy
Drinking Water Infrastructure
Water Infrastructure – Stormwater
Water Infrastructure – Drinking Water
Water Infrastructure – General
Water Infrastructure – Wastewater
Theme 18
Theme 19
Theme 20

## 2.2 Exposure Matrix
Community Assets (Copy from TAB: 2.1 Community Asset Themes) | Climate-Related Hazards
| Hazard A (e.g., Flooding) | Hazard B (e.g., Landslides) | Hazard C (e.g., Wildfire) | Hazard D (e.g., Extreme Weather) | Hazard E (e.g., Heat)
Asset Theme 1
Asset Theme 2
Asset Theme 3
Asset Theme 4
Asset Theme 5
Asset Theme 6
Asset Theme 7
Asset Theme 8
Asset Theme 9
Asset Theme 10

## 2.3 Impact Data Assessment
Potential Impact Pair Document the potential impact pairs (e.g., Wildfire/ Commercial Properties) | Describe the project area (specific to the asset in your potential impact pair). Are you using municipal boundaries or census boundaries or other to create the project area? | What data or information are available for the climate-related hazard (note the scale of the data available)? What is known about the hazard relative to the study area (e.g., probability of the hazard occuring and any historical or future predictions regarding the magnitude of impact)? Spatial data such as a shapefile of the extent of the climate-related hazard. Narrative data such as community member interviews, case studies, new articles, social listening research. | What are the climate stressors associated with the climate-related hazard? If applicable, what are the data sources of the climate stressors (note the scale of the data)? How do you anticipate incorporating this into your analysis? Think about the question you're trying to answer such as 'how would sea level rise affect the assets?'. | What are the non-climate stressors associated with the climate-related hazard? If applicable, what are the data sources of the non-climate stressors (note the scale of the data)? How do you anticipate incorporating this into your analysis? Think about the question you're trying to answer such as 'how does aging infrastructure increase the asset's vulnerability?'. | If applicable, what data/ information is available about the people who may be impacted by the hazard? This is information you will likely copy and paste. | Is there anything in your data/ information that can speak to the sensitivity of the asset theme as it relates to the climate-related hazard? For example, is there an asset type that if harmed by the hazard will have greater consequences than other asset types (such as hospitals compared to open land without any structures)? | Is there anything in your data/ information that can speak to the adaptive capacity of the asset theme as it relates to the climate-related hazard? For example, are there asset characteristics that allow the asset to better handle or avoid the impact of the climate-related hazard (such as buildings built outside of a floodplain or elevated above the base flood elevation)?
Wildfire / Commercial Properties | The project area for the impact of flooding on commercial properties is the 100-year floodplain within the city limits. We are using census tracts to analyze socioeconomic data and municipal boundaries for infrastructure data. | For flooding, we have FEMA flood maps (1:24,000 scale) and local stormwater drainage data. We also have historical archives from the library of community members' experiences during the most damaging storms. Historical records show three major floods in | Sea level rise is a climate stressor for coastal flooding. Data is obtained from NOAA’s Sea Level Calculator. | Increased impervious surfaces from new development are a non-climate stressor for flooding. Data comes from the city’s land-use plans. | Census data shows that the study area has a high population of elderly residents and low-lying households built before 1980. Parcel data from the county assessor’s office provides information on land use and building ownership. GIS data from the city’s | Hospitals are highly sensitive to power outages during extreme heat events as they require continuous operation of life-support systems. | Buildings elevated above the 100-year flood level have a higher adaptive capacity to flooding.

## 2.4 Metadata Collection
Data Type Asset, Hazard, Social Vulnerability | Dataset | Assessment Type Spatial, Narrative | Description of Data Such as dataset file type, format, purpose | Available Information Information included in the dataset | Status Desired, Not Applicable, Unavailable, Collected | File Name Name used in your files | Data Source Hyperlink and or Organization/ Agency Name | Year Created | Year Last Updated If applicable | Collected By | Notes
Asset Data | Project Area Boundary | Spatial | Project boundaries are often spatial polygons indicating the extent of your study area (such as a city boundary) and are often publicly available.
Asset Data | Property Parcels | Spatial | Property parcel data is often available in a spatial dataset such as a shapefile and may have additional spreadsheet data (such as a CSV file) that can be joined to your shapefile using GIS tools. | Indicate the available information provided in the dataset. For property parcel spatial datasets or spreadsheets this could be a list of fields or columns. Information may include but is not limited to geographic information (acreage, geocodes), ownership and ownership history (owner's name, legal description), zoning and land use (land use codes, building details), and taxation and financial data (property tax ID, assessed value, mortgage information).
Asset Data | Building Footprints | Spatial | Building footprint data would be available as spatial polygons. | If either the building footprints or parcel data have a value for first floor elevation (FFE), it will be important to note if FEMA data is being used to assess flooding.
Asset Data | Commercial Properties [INSERT YOUR COMMUNITY ASSET THEME HERE] | Spatial | Commercial property data may be available as supplemental spatial datasets in addition to parcel data. Look for data that includes any commercial uses such as retail, office, restaurant, industrial, and other properties that serve businesses or organizations. | Indicate what information is included for each commercial property. Information may include but is not limited to geographic information (acreage, geocodes), ownership and ownership history (owner's name, legal description), zoning and land use (land use codes, building details), and taxation and financial data (property tax ID, assessed value, mortgage information).
Asset Data | Residential Properties [INSERT YOUR COMMUNITY ASSET THEME HERE] | Spatial | Residential property data may be available as supplemental spatial datasets in addition to parcel data. Look for data that includes any residential uses such as condos, apartment buildings, and affordable housing. | Indicate what information is included for each residential property. Information may include but is not limited to geographic information (acreage, geocodes), ownership and ownership history (owner's name, legal description), zoning and land use (land use codes, building details), and taxation and financial data (property tax ID, assessed value, mortgage information).
Asset Data | Government-Owned Properties [INSERT YOUR COMMUNITY ASSET THEME HERE] | Spatial | Government-owned property data may be available as supplemental spatial datasets in addition to parcel data and could be available from local governments. Look for data that includes any government uses such as municipal buildings. | Indicate what information is included for each government-owned property. Information may include but is not limited to geographic information (acreage, geocodes), ownership and ownership history (owner's name, legal description), zoning and land use (land use codes, building details), and taxation and financial data (property tax ID, assessed value, mortgage information).
Asset Data | Critical Facilities [INSERT YOUR COMMUNITY ASSET THEME HERE] | Spatial | Critical facilities data may be available as supplemental spatial datasets in addition to parcel data and could be available from local governments or other parties. Look for data that includes any government uses such as fire and police stations, medical facilities, schools, and utility and energy facilities. | Indicate what information is included for each critical facility property. Information may include but is not limited to geographic information (acreage, geocodes), ownership and ownership history (owner's name, legal description), zoning and land use (land use codes, building details), and taxation and financial data (property tax ID, assessed value, mortgage information).
Asset Data | Cultural and Community Assets [INSERT YOUR COMMUNITY ASSET THEME HERE] | Spatial | Cultural and community asset data may be available as supplemental spatial datasets in addition to parcel data. Look for data that includes any uses such as parks, local landmarks, civic or community facilities, and religious centers. | Indicate what information is included for each cultural and community asset property. Information may include but is not limited to geographic information (acreage, geocodes), ownership and ownership history (owner's name, legal description), zoning and land use (land use codes, building details), and taxation and financial data (property tax ID, assessed value, mortgage information).
Hazard Data | Riverine Flooding | Spatial
Hazard Data | Community Plans Review | Narrative | Narrative information on past flood impacts may be available in past and current community plans such as hazard mitigation plans, comprehensive plans, and emergency operations plans.
Hazard Data | Pluvial Flooding | Spatial
Hazard Data | Wildfire | Spatial
Hazard Data | Extreme Heat | Spatial
Hazard Data | Extreme Heat | Narrative | Narrative information on extreme heat hazards may be available from state and federal resources such as Heat.gov, NOAA's Climate Explorer, and the National Climate Assessment.
Hazard Data | Drought | Spatial
Social Vulnerability Data | CDC Social Vulnerability Index | Spatial
Social Vulnerability Data | U.S. Census Metrics | Spatial
Social Vulnerability Data | Local Social Vulnerability Data | Spatial

## 2.5 Community Asset Types
Community Asset Theme | Asset Type ID | Layer/Field | Criteria | Notes | High Criticality (yes/ no)
Critical Facilities | police_stations | parcels.shp / USE_CODE | 201 | Use code for law enforcement. | Yes
Critical Facilities | hospitals | parcels.shp / TYPE | Hospital | Separate point layer for key facilities was available. | Yes
Critical Facilities | fire_stations | parcels.shp / USE_CODE | 205 |  | Yes
Critical Facilities | schools | parcels.shp / USE_CODE | 401; 402 | Use code for K-12 and higher education. | Yes
Critical Facilities | substations | utilities.shp / FEATURE | Substation | A failure could impact the entire grid. | Yes
Residential | single_family | parcels.shp / USE_CODE | 101 | Standard single-family homes | No
Residential | multi_family | parcels.shp / USE_CODE | 105; 110 | Includes apartments and condos. High density of people. | Yes
Residential | mobile_homes | parcels.shp / DESC | Contains "Mobile Home" | These structures are often more physically vulnerable. | Yes
Commercial | retail_small | parcels.ship / SQ_FT | < 25000 | Small businesses, important for local economy but less critical than major employers. | No
Commercial | major_employers | businesses.shp / EMPLOYEES | > 250 | A disruption here would have significant economic and job impacts. | Yes
Cultural and Community | historic_sites | landmarks.shp / all | all | Irreplaceable cultural assets | Yes
Cultural and Community | places_of_worship | parcels.shp / USE_CODE | 501 | Often serve as informal community gathering and support centers | No
Cultural and Community | food_bank | social_svcs.shp / SERVICE | Food Pantry | Provides essential services to vulnerable populations | Yes
Natural Systems | parks_open_space | zoning.shp / ZONE | OS | Public green space | No
Natural Systems | wetlands_tidal | NWI.shp / ATTRIBUTE | E2EM | National Wetlands Inventory data. Critical for flood storage and habitat. | Yes

## 3.1 Rulesets
There are ten spaces for ten potential impacts below. Replicate the potential impact box as much as needed to match the number of potential impacts your community is working with.
Potential Impact #1 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #2 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #3 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #4 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #5 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #6 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #7 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #8 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #9 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)
Potential Impact #10 (such as "Flooding impact on critical infrastructure"):
Vulnerability
| Sensitivity | Adaptive Capacity
High | e.g., structure in inundation extent with high criticality | e.g., structure built outside of floodplain or structure in floodplain built after BFE requirements were raised to 1–2ft, 2015
Medium | e.g., structure in inundation extent | e.g., structure in floodplain built after BFE requirements were put in place, 2015
Low | e.g., no structure in inundation extent (land only) | e.g., structure in floodplain built before BFE requirements were put in place, 2015
Risk
| Probability | Magnitude of Impact
High | e.g., Category 1 hurricane extents | e.g., structure exposed
Medium | e.g., Category 2–3 hurricane extents | e.g., left blank in this case
Low | e.g., Category 4–5 hurricane extents | e.g., no structure exposed (land only)

## 4.1 Resilience Obj and Opt
Resilience Objective | Option ID | Resilience Option | Climate-related Hazard | Asset | Action Type | Subaction Type | Source | Local or National Best Practice | Community ID | Local Option (Reworded) | Notes
Resilience Objective 1 Text | EOP-001 | Acquire repeatedly flooded parcels as appropriate and convert into green infrastructure
Resilience Objective 1 Text | EOP-002 | Enhance the protective features of the natural ecosystem
Resilience Objective 1 Text | EOP-003 | Upgrade public assets to minimize services disruptions during acute shocks
Resilience Objective 2 Text | EOP-001 | Acquire repeatedly flooded parcels as appropriate and convert into green infrastructure
Resilience Objective 2 Text | EOP-002 | Enhance the protective features of the natural ecosystem
Resilience Objective 2 Text | EOP-003 | Upgrade public assets to minimize services disruptions during acute shocks
Resilience Objective 3 Text | EOP-001 | Acquire repeatedly flooded parcels as appropriate and convert into green infrastructure
Resilience Objective 3 Text | EOP-002 | Enhance the protective features of the natural ecosystem
Resilience Objective 3 Text | EOP-003 | Upgrade public assets to minimize services disruptions during acute shocks
Resilience Objective 4 Text | EOP-001 | Acquire repeatedly flooded parcels as appropriate and convert into green infrastructure
Resilience Objective 4 Text | EOP-002 | Enhance the protective features of the natural ecosystem
Resilience Objective 4 Text | EOP-003 | Upgrade public assets to minimize services disruptions during acute shocks
Resilience Objective 5 Text | EOP-001 | Acquire repeatedly flooded parcels as appropriate and convert into green infrastructure
Resilience Objective 5 Text | EOP-002 | Enhance the protective features of the natural ecosystem
Resilience Objective 5 Text | EOP-003 | Upgrade public assets to minimize services disruptions during acute shocks

## 5.1 Community Option Prioritize
|  | Reduction of vulnerability and risk |  |  | Ability to implement
Community ID (e.g., FD-01 represents Flooding Downtown Option 1) | Local Option (Reworded) | Criterion #1 (e.g., social equity addressed / co-benefits) | Criterion #2 (e.g., social equity addressed / co-benefits) | Criterion #3 (e.g., social equity addressed / co-benefits) | Criterion #1 (e.g., staff capacity / political will / funding availability / long-term sustainability) | Criterion #2 (e.g., staff capacity / political will / funding availability / long-term sustainability) | Criterion #3 (e.g., staff capacity / political will / funding availability / long-term sustainability) | Strategy Tier # (1–4) (Hover over cell for definitions.) | Notes
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
|  | Select an option | Select an option | Select an option | Select an option | Select an option | Select an option
Note on I2: Tier Definitions Tier 1: High Impact and Feasible These are your “ready-to-go” resilience options. They effectively reduce the community’s vulnerability and risk, and the community already has the ability to implement them. Tier 2: High Impact, but with Barriers These are great ideas with a catch. The resilience options promise to reduce vulnerability and risk, but something is holding them back. The community’s next step for these options is to identify and address those barriers, such as securing funding or building staff capacity. Tier 3: Feasible, but Lower Impact The community can implement these resilience options fairly easily, but these options have a smaller effect on reducing the overall vulnerability and risk. These options might be good “early wins,” but you’ll need to weigh their limited impact against the community’s larger priorities. Tier 4: Lower Impact and Barriers to Implementation These resilience options face challenges on two fronts: they have a lower potential to reduce risk, AND there are barriers to getting them done. These will likely be the community’s lowest-priority options unless the community can find ways to improve both their impact and feasibility.

## OPT 5.1 MASTER STAPLEE Score Sh
Duplicate this tab as needed (i.e., one tab per evaluated action).
ACTION: | Type in the action being evaluated here. |  |  | Total Action Score: | 0
Question # | Question/Criteria | Considerations | Scoring Values | Score
SOCIAL |  |  |  |  | FINAL SOCIAL SCORE: | 0
1 | How critical is the proposed project to the entire community? | Consider public safety, health, economic, environmental, or other reasons and extent of "community." | Critical to entire county or entire municipality: 4 Critical to north, central, or south end: 3 Critical to one neighborhood or area: 2 Not very critical: 1 Minimal: 0
2 | Does the project mitigate a health or safety issue in the community? Note: Mitigation reduces or eliminates loss of life or property in future disasters (not simply restoration to normal). | Consider effects on local waters where people swim and fish; reduced risk of flooding, fire, etc.; removal of debris that attracts rodents and can become airborne in high winds; reduced risk of traffic accidents | Yes: 1 No: 0
3 | If the hazard for which the project proposes to mitigate should occur prior to implementation of the proposed project, are the anticipated impacts of the hazard likely to result in an immediate need? | Consider impacts from previous disasters, such as number of people affected and other economic considerations. | Yes: 1 No: 0
4 | Does the proposed project benefit a critical facility, critical infrastructure, or a road that is the only entrance and exit? | List of critical facilities (fire stations, EMS, hospitals), buildings that serve as shelters, nursing homes, and goverment offices; utility infrastructure; roads | Yes: 1 No: 0
5 | Does the proposed project have (or can it easily gain) the support and acceptance of the impacted community, and is it compatible with present and future community values? | Consider comments from residents and community organizations, newspaper articles and electronic media, and community plans. For community values, consider community plans, local newspapers, HOA websites, etc. | Public has expressed uniform support: 1 Public has expressed no opinion or mixed opinion: 0 Public has expressed uniform opposition: -1
6 | Will the proposed project adversely affect minority and low-income populations? | Use demographic maps and other information to look for disproportionate adverse effects. | Yes: -1 No: 1
7 | What effects will the proposed project have on cultural, tribal, archeological, or historical resources (known or suspected) within the area? | Consult with state historic preservation office and cultural and preservation groups. | Positive effects: 1 No effects: 0 Negative effects: -1
TECHNICAL |  |  |  |  | FINAL TECHNICAL SCORE: | 0
8 | Is the proposed project technically feasible considering, for example, acquisition of right-of-way easements or property that may be necessary? | What are the best practices for engineering and public works? Acquisition of land or easements is considered an extraordinary action. | Feasible with no extraordinary actions: 1 Feasible with extraordinary actions: -1 Not feasible at all: -2
9 | How effective is the proposed project in avoiding or reducing future losses for the long term? | Consider information on reptitive losses and how the project will mitigate against future losses. | Extremely effective: 2 Effective: 1 Not effective: 0
10 | Will the proposed project impact utilities or transportation systems? | Is there an existing need for utilities to be upgraded or replaced? Could there be co-benefits such as adding sidewalks as a "goes with" project? | Positive impact: 1 No impact: 0 Negative impact: -1
11 | Will the proposed project create more problems than it solves? | Consider, for example, if a property is purchased and converted into a vacant lot. Will a vacant lot in a neighborhood give rise to other problems, such as dumping? In this case, the problem is solved for one homeowner, but another problem is created for a neighborhood. These are considered unintended consequences of an action. | No: 1 Unknown: 0 Yes: -1
12 | Does the proposed project solve the problem or only a symptom of the problem? | Consider if the action is just a short-term solution or if it addresses long-term vulnerabilities and risks. | Solves the problem: 2 Solves a sympton: 1
13 | How long will it take to complete the project, and is the time frame reasonable? | Touch base with relevant staff or contractors to make an estimate; different types of projects will likely have different timelines, needs, and expectations. | Less than two years/reasonable time frame: 2 Less than 4 years/reasonable time frame: 1 More than 4 years/unreasonable time frame: 0 Unreasonable time frame: -1
14 | Is technical expertise available and at what cost? | Touch base with relevant staff or contractors to determine if specific skillsets are needed on the project and estimate the cost of their services. | Project can be done in-house without consultants: 2 Consultants must be hired, but cost is reasonable: 1 Consultants must be hired and cost is extremely high: 0
ADMINISTRATIVE |  |  |  |  | FINAL ADMINISTRATIVE SCORE: | 0
15 | Does the entity have the capability (staff, expertise, time, funding) to implement the proposed project? If not, what is lacking? | Consider what the project will require of the staff for the entire duration of project implementation. Touch base with relevant staff for their insight. | Yes: 1 Unknown or not applicable: 0 No: -1
16 | Can the entity provide necessary maintenance of the proposed project in terms of funding, staffing, and other resources? | Consider the long-term needs of the project after implementation. What will be needed to ensure the project continues to be successful? | Yes: 1 Unknown or not applicable: 0 No: -1
17 | Can the proposed project be accomplished in a timely manner without a drain on entity resources? | Consider whether other responsibilities or projects will suffer or if the entity has the ability to add capacity to accomplish the project. | Yes: 1 Unknown: 0 No: -1
POLITICAL |  |  |  |  | FINAL POLITICAL SCORE: | 0
18 | Have political leaders participated in the planning process? Is there a local champion willing to help see the proposed project to completion? | Consider the political will within the community or whether and how easily it could be influenced. | Yes to both political participation and local champion: 2 Yes to either political participation or local champion: 1 Unknown: 0 Political leaders opposed: -1
19 | Who are the stakeholders in the project, and have all stakeholders been offered an opportunity to participate in the planning process? | Stakeholders are residents, community organizations, representatives of different local governments, businesses, schools, etc. | All stakeholders have been involved: 2 Some stakeholders have been involved: 1 No stakeholders have been involved: 0
20 | Will the proposed project comply with the comprehensive plan and land use elements, zoning activities, and transportation, environmental, flood zone, historical, and other long-range plans? | Touch base with relevant staff to learn more about known plans and determine compliance with plans. | Yes to all plans: 2 Yes to some plans: 1 Unknown: 0 Out of compliance with at least one plan: -1
21 | Does the proposed project accomplish the desired objective at the "lowest" cost price to the public? | Consider multiple types of costs (e.g., monetary, construction-related, unintended consequences, etc.). | Yes: 1 Unknown: 0 No: -1
LEGAL |  |  |  |  | FINAL LEGAL SCORE: | 0
22 | Does the proposing entity have the authority to implement the project? | Consider land ownership and if the proposing entity will need to partner with other organizations or agencies. | Has authority: 1 Does not have authority: -1
23 | Do HOA bylaws apply to the project? | If the project is in an area with an HOA, consider the bylaws and if any action is needed. | HOA bylaws apply and allow the project: 1 HOA bylaws do not apply: 1 HOA bylaws apply and do not allow the project without an amendment: -1 HOA bylaws apply and do not allow the project: -2
24 | Will the proposed project comply with local, state, and federal regulations? |  | Yes: 1 No: -1
25 | Are the proper laws, ordinances, and resolutions in place to implement the proposed project? | Consider if an amendment is needed before the project can move forward. | Yes: 1 No, but amendments are possible to bring the project into compliance: 0 No, and amendments are not likely: -1
26 | Are there potential legal consequences, or is the proposed project likely to be challenged by stakeholders who may be affected? | Consider the potential for lack of compliance with existing laws and the protential for legal opposition. | No: 1 Maybe or unknown: 0 Yes: -1
ECONOMIC |  |  |  |  | FINAL ECONOMIC SCORE: | 0
27 | Is funding currently available to implement the proposed project? | Consider if the project is included in a capital improvements program (CIP) or budget in the first year or later years or if it will be added. Fund sources might be local government revenue, grants, donations from private sources, or a combination. | Yes, full funding is committed within the first year: 3 Yes, funding is spread over a few years: 2 Partial funds have been identified: 1 No funds have been identified: 0
28 | Does the cost of the project seem reasonable for the size of the problem and likely benefits? | Consider if a cost estimate has been completed. If not, rely upon the best engineering and public works expertise available. | Yes, and a cost estimate has been completed: 1 Yes, but a cost estimate has not been completed: 0 No, the project cost seems to be unreasonable for the size of the problem and the likely benefits: -1
29 | Has a benefit-cost analysis (BCA) been conducted, and can a positive cost-effectiveness ratio be demonstrated? | If the project is set to be federally funded, it must be shown to be cost effective. | Yes to both: 2 A BCA has not been conducted: 0 A BCA has not been conducted, and the cost-effectiveness ratio is less than one: -1
30 | What burden will be placed on the tax base or local economy to implement and maintain the proposed project? | Consider if funds must come from local government revenues. Determine how much would constitute a reasonable versus excessive burden to implement and maintain. | No burden to implement and maintain: 1; Reasonable burden to implement and maintain: 0; Excessive burden to implement and maintain: -1
31 | Does the proposed project contribute to other community economic goals, such as improvements or economic development? Will the proposed project generate additional permanent jobs locally? | Consider job creation from construction, demolition, operations, etc. Does the project influence a specific kind of development within the area or something else? | Does contribute: 1 Not applicable, unknown, or no effect): 0 Negative effect: -1
ENVIRONMENTAL |  |  |  |  | FINAL ENVIRONMENTAL SCORE: | 0
32 | How will the proposed project affect the environment (water, land, endangered species, etc.)? | Touch base with relevant staff, organizations, agencies, etc. to understand effects. | Positive effect: 1 Unknown or no effect: 0 Negative effect: -1
33 | Will the proposed project comply with local, state, and federal environmental laws and regulations? | Touch base with relevant experts in the field to determine compliance. | Yes: 1 Unknown: 0 No: -1
34 | Is the proposed project in a floodplain or wetland, or will the project directly impact the natural and beneficial functions of a floodplain or wetland? | Cross-reference the project site with existing floodplain and wetland maps; if not in a floodplain, consider if the project will in some way affect a floodplain or wetland area. | Will benefit a floodplain or wetland: 1 Not applicable, unknown, or no effect: 0 Negative effect on floodplain or wetland: -1
35 | Does the project involve issues on a coastal barrier island or coastal high hazard area? | Consider the complexities of developing on coastal barrier islands and best practices. | Yes, but the outcome is positive: 1 Not applicable, unknown, or no effect: 0 Negative effect: -1
36 | What effects or impacts will the proposed project have on the quality of surface waters? | Consider water quality and volume. | Positive effect on surface waters: 1 Not applicable, unknown, or no effect: 0 Negative effect on surface waters: -1
37 | Is the proposed project consistent with community environmental goals? | Consider the comprehensive plan and community plans or the value the community puts on clean water for drinking and recreation, clean air, heritage trees, proper siting and management of landfills, and lands for hunting and other types of recreation. | Consistent with environmental goals: 1 Not applicable, unknown, or no effect: 0 Inconsistent with environmental goals: -1